## Gantt Chart
E-Commerce Data Warehouse
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project start date: | 2025-01-06 |  |  |  |  | January | [27 empty] | February
Scrolling increment: | 0 | time axis 2025-01-06 to 2025-03-14
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2025-01-06 to 2025-03-14
Requirement Analysis
Identify key stakeholders | On Track | Name | 100% | 2025-01-06 | 1
Gathering stakeholder and business requirements | On Track |  | 100% | 2025-01-06 | 2
Source system analysis (architecture, data, data type) | On Track |  | 100% | 2025-01-08 | 7
Completing project charter | On Track |  | 100% | 2025-01-15 | 2
Initial stakeholder alignment | Milestone |  | 100% | 2025-01-17 | 1 | bar: 2025-01-17
Data Modelling
Designing dim tables | Low Risk |  | 60% | 2025-01-20 | 3
Designing fact tables | Med Risk |  | 50% | 2025-01-20 | 3
Designing summary and snapshot fact tables | High Risk |  | 33% | 2025-01-23 | 1
Stakeholder alignment | Milestone |  |  | 2025-01-24 | 1 | bar: 2025-01-24
ETL Implementation
ETL for the dim tables | On Track |  |  | 2025-01-27 | 5
ETL for the fact tables | On Track |  |  | 2025-01-27 | 9
ETL for the summary fact tables | On Track |  |  | 2025-02-05 | 2
Stakeholder alignment on logic | Milestone |  |  | 2025-02-07 | 1 | bar: 2025-02-07
Testing and Validation
Initial testing (low-volume data) | On Track |  |  | 2025-02-10 | 3
Possible debugging | On Track |  |  | 2025-02-10 | 5
Volume testing (high-volume) | On Track |  |  | 2025-02-17 | 3
Possible debugging and optimization | On Track |  |  | 2025-02-17 | 5
User Acceptance Test
Production testing for selected users | On Track |  |  | 2025-02-24 | 5
Feedback alignment | On Track |  |  | 2025-03-03 | 1
Actions for feedback | On Track |  |  | 2025-03-03 | 5
Deployment and Cascade
Process and technical documentation | On Track |  |  | 2025-03-10 | 4
DW Cascade to all users | On Track |  |  | 2025-03-14 | 1
Closing the project | Milestone |  |  | 2025-03-14 | 1 | bar: 2025-03-14

## Metadata
Attribute Name | Definition | Data Mart | Table Name | Column | Data Type | Description | Logic
order_key | Surrogate key to identify the order and also be used as foreign key to identify order details | Marketplace | fact_platform_peformance_summary | date_key | bigint | Foreign key to the dim_date table, representing the relevant date for time-series metrics | distinct date_key_ from mdm.fact_order_detail
buyer_key | Foreign key linking to the dim_buyer table to identify order's buyer | Marketplace | fact_platform_peformance_summary | l1d_ado | decimal(12,4) | Average daily orders for the last 1 day | count(order_key)/1.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date = current_date - interval '1 day'
seller_key | Foreign key linking to the dim_seller table to identify the order's seller | Marketplace | fact_platform_peformance_summary | l7d_ado | decimal(12,4) | Average daily orders for the last 7 days | count(order_key)/7.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date between current_date - interval '7 days' and current_date - interval '1 day'
voucher_mix_key | Foreign key linking to the dim_voucher_mix table to identify any voucher mix used in the order | Marketplace | fact_platform_peformance_summary | l30d_ado | decimal(12,4) | Average daily orders for the last 30 days | count(order_key)/30.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date between current_date - interval '30 days' and current_date - interval '1 day'
voucher_total_value | Total value of all used vouchers for the order | Marketplace | fact_platform_peformance_summary | l1d_adgmv | decimal(12,4) | Average daily GMV for the last 1 day | sum(gmv)/1.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date = current_date - interval '1 day'
payment_option_key | Foreign key linking to the dim_payment_option tableto identify payment method | Marketplace | fact_platform_peformance_summary | l7d_adgmv | decimal(12,4) | Average daily GMV for the last 7 days | sum(gmv)/7.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date between current_date - interval '7 days' and current_date - interval '1 day'
shipping_fee | Amount of total shipping fee cost paid by buyer | Marketplace | fact_platform_peformance_summary | l30d_adgmv | decimal(12,4) | Average daily GMV for the last 30 days | sum(gmv)/30.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date between current_date - interval '30 days' and current_date - interval '1 day'
gmv | Gross merchandise value which is the total value of the goods | Marketplace | fact_platform_peformance_summary | l1d_avg_active_buyers | decimal(12,4) | Average number of active buyers per day in the last 1 day | count(distinct buyer_key)/1.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date = current_date - interval '1 day'
order_create_date_key | Foreign key to the dim_date table to identify order's create date | Marketplace | fact_platform_peformance_summary | l7d_avg_active_buyers | decimal(12,4) | Average number of active buyers per day in the last 7 days | count(distinct buyer_key)/7.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date between current_date - interval '7 days' and current_date - interval '1 day'
order_create_time_key | Foreign key to the dim_time table to identify order's create timestamp | Marketplace | fact_platform_peformance_summary | l30d_avg_active_buyers | decimal(12,4) | Average number of active buyers per day in the last 30 days | count(distinct buyer_key)/7.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date between current_date - interval '30 days' and current_date - interval '1 day'
unique_sku_count | Number of distinct SKUs in the order | Marketplace | fact_platform_peformance_summary | l1d_avg_active_shops | decimal(12,4) | Average number of active shops per day in the last 1 day | count(distinct seller_key)/1.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date = current_date - interval '1 day'
total_sky_qty | Total quantity of items in the order | Marketplace | fact_platform_peformance_summary | l7d_avg_active_shops | decimal(12,4) | Average number of active shops per day in the last 7 days | count(distinct seller_key)/7.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date between current_date - interval '7 days' and current_date - interval '1 day'
wh_key | Foreign key linking to the dim_warehouse table to identify the assigned warehouse, if any | Marketplace | fact_platform_peformance_summary | l30d_avg_active_shops | decimal(12,4) | Average number of active shops per day in the last 30 days | count(distinct seller_key)/7.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date between current_date - interval '30 days' and current_date - interval '1 day'
parcel_count | Number of parcels for the order | Marketplace | fact_platform_peformance_summary | l1d_otd_time | decimal(12,4) | Average on-time delivery time (in hours) for the last 1 day | (delivered_time_key - order_create_time_key)/(count(parcel_id) * 3600.0000) from mdm.fact_parcel_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where a.delivered_time_key is not null and b.date = current_date - interval '1 day'
forder_key | Unique identifier for the order fulfilment | Warehouse | fact_platform_peformance_summary | l7d_otd_time | decimal(12,4) | Average on-time delivery time (in hours) for the last 7 days | (delivered_time_key - order_create_time_key)/(count(parcel_id) * 3600.0000) from mdm.fact_parcel_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where a.delivered_time_key is not null and b.date between current_date - interval '7 days' and current_date - interval '1 day'
shipping_channel_key | Foreign key linking to the dim_shipping_channel table to identify the order's delivery method | Warehouse | fact_platform_peformance_summary | l30d_otd_time | decimal(12,4) | Average on-time delivery time (in hours) for the last 30 days | (delivered_time_key - order_create_time_key)/(count(parcel_id) * 3600.0000) from mdm.fact_parcel_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where a.delivered_time_key is not null and b.date between current_date - interval '30 days' and current_date - interval '1 day'
parcel_status_key | Foreign key linking to the dim_parcel_status table to identify the order's latest status
pickup_time_key | Foreign key to the dim_time table to identify the order's time of picked up
cancel_time_key | Foreign key to the dim_time table to identify the order's time of cancellation
delivered_time_key | Foreign key to the dim_time table to identify the order's time of delivery
ship_by_date_key | Foreign key to the dim_time table to identify the order's target date of shipping
total_sku_count | Total number of distinct SKUs for the order
date_key | Foreign key to the dim_date table, representing the relevant date for time-series metrics
l1d_ado | Average daily orders for the last 1 day
l7d_ado | Average daily orders for the last 7 days
l30d_ado | Average daily orders for the last 30 days
l1d_adgmv | Average daily GMV for the last 1 day
l7d_adgmv | Average daily GMV for the last 7 days
l30d_adgmv | Average daily GMV for the last 30 days
l1d_avg_active_buyers | Average number of active buyers per day in the last 1 day
l7d_avg_active_buyers | Average number of active buyers per day in the last 7 days
l30d_avg_active_buyers | Average number of active buyers per day in the last 30 days
l1d_avg_active_shops | Average number of active shops per day in the last 1 day
l7d_avg_active_shops | Average number of active shops per day in the last 7 days
l30d_avg_active_shops | Average number of active shops per day in the last 30 days
l1d_otd_time | Average on-time delivery time (in hours) for the last 1 day
l7d_otd_time | Average on-time delivery time (in hours) for the last 7 days
l30d_otd_time | Average on-time delivery time (in hours) for the last 30 days
wh_id | Identification for warehouse (natural key)
wh_name | Designated name of the warehouse
wh_region | Warehouse's geographic region address
wh_city | Warehouse's city address
wh_brgy | Warehouse's barangay address
wh_postal_code | Postal code of the warehouse's location
total_land_area | Total land area of the warehouse in sq meters
operating_hours | Operational warehouse of the warehouse
is_active | 1 if active, 0 if not operational

## Data Layer
Table Type | Data Mart | Table Name
Dim | MDM | dim_order
Dim | MDM | dim_order_parcel
Dim | MDM | dim_parcel_status
Dim | MDM | dim_time
Dim | MDM | dim_date
Dim | MDM | dim_shipping
Dim | MDM | dim_operator
Dim | MDM | dim_location
Dim | MDM | dim_payment
Dim | MDM | dim_item
Dim | MDM | dim_seller
Dim | MDM | dim_buyer
Dim | MDM | dim_voucher
Dim | MDM | dim_voucher_mix
Fact - Detail | MDM | fact_order_detail
Fact - Detail | MDM | fact_parcel_detail
Fact - Detail | MDM | fact_order_item_detail
Fact - Snapshot | MDM | fact_parcel_status_snapshot
Fact - Summary | MDM | fact_platform_performance_summary
Fact - Summary | MDM | fact_sku_performance_summary
Fact - Summary | MDM | fact_seller_performance_summary
Dim | WDM | dim_warehouse
Dim | WDM | dim_task
Dim | WDM | dim_staff
Dim | WDM | dim_supplier
Dim | WDM | dim_storage
Dim | WDM | dim_purchase_order_asn
Fact - Detail | WDM | fact_outbound_task_detail
Fact - Detail | WDM | fact_outbound_sku_detail
Fact - Detail | WDM | fact_outbound_order_detail
Fact - Detail | WDM | fact_inbound_task_detail
Fact - Detail | WDM | fact_inbound_sku_detail
Fact - Snapshot | WDM | fact_storage_inventory_snapshot
Fact - Snapshot | WDM | fact_attendance_snapshot
Fact - Summary | WDM | fact_staff_prod_summary
Fact - Summary | WDM | fact_warehouse_summary

## High Level S2T
Row | System Source | Source Table | Target Data Mart | Target Table
1 | OMS | order | MDM | dim_order
2 | OMS | order | MDM | dim_order_parcel
3 | OMS | fulfillment | MDM | dim_parcel_status
4 | WMS | outbound_order | MDM | dim_parcel_status
5 |  |  | MDM | dim_time
6 |  |  | MDM | dim_date
7 | OMS | courier | MDM | dim_shipping
8 | OMS | fulfillment | MDM | dim_operator
9 | OMS | courier | MDM | dim_operator
10 | OMS | fulfillment | MDM | dim_location
11 | UMS | delivery_detail | MDM | dim_location
12 | UMS | pickup_location | MDM | dim_location
13 | UMS | user | MDM | dim_location
14 | Flat File Ingestion | wh_information_ingestion | MDM | dim_location
15 | UMS | payment_option | MDM | dim_payment
16 | LPMS | item | MDM | dim_item
17 | LPMS | listing | MDM | dim_item
18 | UMS | seller | MDM | dim_item
19 | UMS | seller | MDM | dim_seller
20 | UMS | user | MDM | dim_seller
21 | UMS | user | MDM | dim_buyer
22 | LPMS | voucher | MDM | dim_voucher
23 | LPMS | voucher_redemption | MDM | dim_voucher_mix
24 | LPMS | voucher | MDM | dim_voucher_mix
25 | OMS | order | MDM | fact_order_detail
26 | OMS | item | MDM | fact_order_detail
27 | WMS | outbound_order | MDM | fact_order_detail
28 | LPMS | voucher_redemption | MDM | fact_order_detail
29 | OMS | order | MDM | fact_parcel_detail
30 | OMS | item | MDM | fact_parcel_detail
31 | WMS | outbound_order | MDM | fact_parcel_detail
32 | OMS | fulfillment | MDM | fact_parcel_detail
33 | OMS | order | MDM | fact_order_item_detail
34 | OMS | item | MDM | fact_order_item_detail
35 | WMS | outbound_task | MDM | fact_order_item_detail
36 | OMS | fulfillment | MDM | fact_parcel_status_snapshot
37 | MDM | fact_order_detail | MDM | fact_platform_performance_summary
38 | MDM | fact_order_item_detail | MDM | fact_sku_performance_summary
39 | MDM | fact_order_detail | MDM | fact_seller_performance_summary
40 | Flat File Ingestion | wh_information_ingestion | WDM | dim_warehouse
41 | WMS | outbound_task | WDM | dim_task
42 | WMS | inbound_task | WDM | dim_task
43 | WMS | staff | WDM | dim_staff
44 | WMS | supplier | WDM | dim_supplier
45 | WMS | storage | WDM | dim_storage
46 | WMS | inbound_order | WDM | dim_purchase_order_asn
47 | WMS | purchase_order | WDM | dim_purchase_order_asn
48 | WMS | outbound_task | WDM | fact_outbound_task_detail
49 | WMS | outbound_order | WDM | fact_outbound_sku_detail
50 | WMS | outbound_task | WDM | fact_outbound_sku_detail
51 | WMS | outbound_order | WDM | fact_outbound_order_detail
52 | WMS | inbound_task | WDM | fact_inbound_task_detail
53 | WMS | inbound_order | WDM | fact_inbound_sku_detail
54 | WMS | purchase_order | WDM | fact_inbound_sku_detail
55 | WMS | storage | WDM | fact_storage_inventory_snapshot
56 | WMS | attendance | WDM | fact_attendance_snapshot
57 | WDM | fact_attendance_snapshot | WDM | fact_staff_prod_summary
58 | WDM | outbound_task | WDM | fact_staff_prod_summary
59 | WDM | inbound_task | WDM | fact_staff_prod_summary
60 | WDM | outbound_order | WDM | fact_warehouse_summary
61 | WDM | outbound_task | WDM | fact_warehouse_summary
62 | WDM | fact_staff_prod_summary | WDM | fact_warehouse_summary

## Detailed S2T
ROW | TARGET | [6 empty] | SOURCE | [6 empty] | HISTORY |  |  |  |  | SCD Type 2: Versioning (Preserving History) Description: Creates a new record for each change, preserving the old record as history. Implementation: Add fields for effective date, end date, or current flag. Use Case: Common for tracking historical changes in data. Example: Tracking changes in an employee's department over time.
| Data Mart | Warehouse Table | Attribute Name | Definition | Sample Values | Target Data Type | Target Length | Nullable | Source System | Source File/Table | Source Field/Column | Source Data Type | Source Length | Transformation Rule | Analytical or Detail | Run Frequency | Insert Into/Overwrite | Change Frequency | History Strategy Type
1 | Marketplace | fact_order_detail | order_key | Surrogate key to identify the order and also be used as foreign key to identify order details | 1,2,3 | bigint | 19 | N | OMS, MDM | oms.order, mdm.dim_order | order_id, order_key | bigint, bigint | 19, 19 | order_key from oms.order join on mdm.dim_order using (order_id) | Detail | Daily | Insert Into | N/A | N/A
2 | Marketplace | fact_order_detail | buyer_key | Foreign key linking to the dim_buyer table to identify order's buyer | 1,2,3 | int | 10 | N | OMS, MDM | oms.order, mdm.dim_buyer | buyer_id, buyer_key | bigint, int | 19, 10 | buyer_key from oms.order join on mdm.dim_buyer using (buyer_id) | Detail | Daily | Insert Into | N/A | N/A
3 | Marketplace | fact_order_detail | seller_key | Foreign key linking to the dim_seller table to identify the order's seller | 1,2,3 | int | 10 | N | OMS, MDM | oms.order, mdm.dim_seller | seller_id, seller_key | bigint, int | 19, 10 | seller_key from oms.order join on mdm.dim_seller using (seller_id) | Detail | Daily | Insert Into | N/A | N/A
4 | Marketplace | fact_order_detail | voucher_mix_key | Foreign key linking to the dim_voucher_mix table to identify any voucher mix used in the order | 1,2,3 | bigint | 19 | Y | OMS, LPMS, MDM | oms.order, lpms.voucher_redemption, mdm.dim_voucher_mix | order_id, voucher_id, voucher_mix_key | bigint, bigint, bigint | 19, 19, 19 | voucher_mix_key from oms.order join on lpms.voucher_redemption using (order_id) join on mdm.dim_voucher_ms using (voucher_id) | Detail | Daily | Insert Into | N/A | N/A
5 | Marketplace | fact_order_detail | voucher_total_value | Total value of all used vouchers for the order | 1.0000, 100.0000, 100000.0000 | decimal | (10, 4) | Y | OMS, LPMS | oms.order, lpms.voucher_redemption | order_id, redeemed_amount | bigint, decimal | 19, (10, 4) | sum(redeemed_amount) from oms.order join on lpms.voucher_redemption using (order_id) | Detail | Daily | Insert Into | N/A | N/A
6 | Marketplace | fact_order_detail | payment_option_key | Foreign key linking to the dim_payment_option tableto identify payment method | 1,2,3 | bigint | 19 | N | OMS, MDM | oms.order, mdm.dim_seller | payment_option_id, payment_option_key | bigint, bigint | 19, 19 | payment_option_key from oms.order join on mdm.dim_payment using (payment_option_id) | Detail | Daily | Insert Into | N/A | N/A
7 | Marketplace | fact_order_detail | shipping_fee | Amount of total shipping fee cost paid by buyer | 1.0000, 100.0000, 100000.0000 | decimal | (10, 4) | N | OMS | oms.order | shipping_fee | decimal | (10, 4) | order from oms.order | Detail | Daily | Insert Into | N/A | N/A
8 | Marketplace | fact_order_detail | gmv | Gross merchandise value which is the total value of the goods | 1.0000, 100.0000, 100000.0000 | decimal | (10, 4) | N | OMS | oms.order | gmv | decimal | (10, 4) | gmv from oms.order | Detail | Daily | Insert Into | N/A | N/A
9 | Marketplace | fact_order_detail | order_create_date_key | Foreign key to the dim_date table to identify order's create date | 1,2,3 | bigint | 19 | N | OMS, MDM | oms.order, mdm.dim_date | order_create_time, date_key | timestamp, bigint | _, 19 | date_key from oms.order a join on mdm.dim_date b on date(a.order_create_time) = b.date | Detail | Daily | Insert Into | N/A | N/A
10 | Marketplace | fact_order_detail | order_create_time_key | Foreign key to the dim_time table to identify order's create timestamp | 1,2,3 | bigint | 19 | N | OMS, MDM | oms.order, mdm.dim_time | order_create_time, time_key | timestamp, bigint | _, 19 | time_key from oms.order a join on mdm.dim_time b on a.order_create_time = b.timestamp | Detail | Daily | Insert Into | N/A | N/A
11 | Marketplace | fact_order_detail | unique_sku_count | Number of distinct SKUs in the order | 1,2,3 | smallint | 5 | N | OMS | oms.item | sku_id | varchar | 20 | count(distint sku_id) from oms.item group by order_id | Detail | Daily | Insert Into | N/A | N/A
12 | Marketplace | fact_order_detail | total_sky_qty | Total quantity of items in the order | 1,2,3 | smallint | 5 | N | OMS | oms.item | qty | smallint | 5 | sum(qty) from oms.item group by order_id | Detail | Daily | Insert Into | N/A | N/A
13 | Marketplace | fact_order_detail | wh_key | Foreign key linking to the dim_warehouse table to identify the assigned warehouse, if any | 1,2,3 | smallint | 3 | Y | OMS, WMS, WDM | oms.order, wms.outbound_order, wdm.dim_warehouse | wh_id, wh_key | smallint, smallint | 3, 3 | wh_key from oms.order left join wms.oubound_order using (order_id) left join wdm.dim_warehouse using (wh_id) | Detail | Daily | Insert Into | N/A | N/A
14 | Marketplace | fact_order_detail | parcel_count | Number of parcels for the order | 1,2,3 | smallint | 3 | N | OMS | oms.order | parcel_id | bigint | 19 | count(parcel_id) from oms.order | Detail | Daily | Insert Into | N/A | N/A
15 | Marketplace | fact_platform_peformance_summary | date_key | Foreign key to the dim_date table, representing the relevant date for time-series metrics | 1,2,3 | bigint | 19 | N | MDM | mdm.fact_order_detail, mdm.dim_date | date_key | bigint | 19 | distinct date_key_ from mdm.fact_order_detail | Detail | Daily | Insert Into | N/A | N/A
16 | Marketplace | fact_platform_peformance_summary | l1d_ado | Average daily orders for the last 1 day | 1000000.1234, 10000000.1234, 10000000.1234 | decimal | (12, 4) | N | MDM | mdm.fact_order_detail, mdm.dim_date | order_key, date_key | bigint, bigint | 19, 19 | count(order_key)/1.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date = current_date - interval '1 day' | Analytical | Daily | Insert Into | N/A | N/A
17 | Marketplace | fact_platform_peformance_summary | l7d_ado | Average daily orders for the last 7 days | 1000000.1234, 10000000.1234, 10000000.1234 | decimal | (12, 4) | N | MDM | mdm.fact_order_detail, mdm.dim_date | order_key, date_key | bigint, bigint | 19, 19 | count(order_key)/7.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date between current_date - interval '7 days' and current_date - interval '1 day' | Analytical | Daily | Insert Into | N/A | N/A
18 | Marketplace | fact_platform_peformance_summary | l30d_ado | Average daily orders for the last 30 days | 1000000.1234, 10000000.1234, 10000000.1234 | decimal | (12, 4) | N | MDM | mdm.fact_order_detail, mdm.dim_date | order_key, date_key | bigint, bigint | 19, 19 | count(order_key)/30.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date between current_date - interval '30 days' and current_date - interval '1 day' | Analytical | Daily | Insert Into | N/A | N/A
19 | Marketplace | fact_platform_peformance_summary | l1d_adgmv | Average daily GMV for the last 1 day | 10000000.1234, 100000000.1234, 100000000.1234 | decimal | (15, 4) | N | MDM | mdm.fact_order_detail, mdm.dim_date | gmv, date_key | decimal, bigint | (10, 4), 19 | sum(gmv)/1.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date = current_date - interval '1 day' | Analytical | Daily | Insert Into | N/A | N/A
20 | Marketplace | fact_platform_peformance_summary | l7d_adgmv | Average daily GMV for the last 7 days | 10000000.1234, 100000000.1234, 100000000.1234 | decimal | (15, 4) | N | MDM | mdm.fact_order_detail, mdm.dim_date | gmv, date_key | decimal, bigint | (10, 4), 19 | sum(gmv)/7.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date between current_date - interval '7 days' and current_date - interval '1 day' | Analytical | Daily | Insert Into | N/A | N/A
21 | Marketplace | fact_platform_peformance_summary | l30d_adgmv | Average daily GMV for the last 30 days | 10000000.1234, 100000000.1234, 100000000.1234 | decimal | (15, 4) | N | MDM | mdm.fact_order_detail, mdm.dim_date | gmv, date_key | decimal, bigint | (10, 4), 19 | sum(gmv)/30.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date between current_date - interval '30 days' and current_date - interval '1 day' | Analytical | Daily | Insert Into | N/A | N/A
22 | Marketplace | fact_platform_peformance_summary | l1d_avg_active_buyers | Average number of active buyers per day in the last 1 day | 1000000.1234, 10000000.1234, 10000000.1234 | decimal | (12, 4) | N | MDM | mdm.fact_order_detail, mdm.dim_date | buyer_key, date_key | int, bigint | 10, 19 | count(distinct buyer_key)/1.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date = current_date - interval '1 day' | Analytical | Daily | Insert Into | N/A | N/A
23 | Marketplace | fact_platform_peformance_summary | l7d_avg_active_buyers | Average number of active buyers per day in the last 7 days | 1000000.1234, 10000000.1234, 10000000.1234 | decimal | (12, 4) | N | MDM | mdm.fact_order_detail, mdm.dim_date | buyer_key, date_key | int, bigint | 10, 19 | count(distinct buyer_key)/7.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date between current_date - interval '7 days' and current_date - interval '1 day' | Analytical | Daily | Insert Into | N/A | N/A
24 | Marketplace | fact_platform_peformance_summary | l30d_avg_active_buyers | Average number of active buyers per day in the last 30 days | 1000000.1234, 10000000.1234, 10000000.1234 | decimal | (12, 4) | N | MDM | mdm.fact_order_detail, mdm.dim_date | buyer_key, date_key | int, bigint | 10, 19 | count(distinct buyer_key)/7.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date between current_date - interval '30 days' and current_date - interval '1 day' | Analytical | Daily | Insert Into | N/A | N/A
25 | Marketplace | fact_platform_peformance_summary | l1d_avg_active_shops | Average number of active shops per day in the last 1 day | 1000000.1234, 10000000.1234, 10000000.1234 | decimal | (12, 4) | N | MDM | mdm.fact_order_detail, mdm.dim_date | seller_key, date_key | int, bigint | 10, 19 | count(distinct seller_key)/1.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date = current_date - interval '1 day' | Analytical | Daily | Insert Into | N/A | N/A
26 | Marketplace | fact_platform_peformance_summary | l7d_avg_active_shops | Average number of active shops per day in the last 7 days | 1000000.1234, 10000000.1234, 10000000.1234 | decimal | (12, 4) | N | MDM | mdm.fact_order_detail, mdm.dim_date | seller_key, date_key | int, bigint | 10, 19 | count(distinct seller_key)/7.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date between current_date - interval '7 days' and current_date - interval '1 day' | Analytical | Daily | Insert Into | N/A | N/A
27 | Marketplace | fact_platform_peformance_summary | l30d_avg_active_shops | Average number of active shops per day in the last 30 days | 1000000.1234, 10000000.1234, 10000000.1234 | decimal | (12, 4) | N | MDM | mdm.fact_order_detail, mdm.dim_date | seller_key, date_key | int, bigint | 10, 19 | count(distinct seller_key)/7.0000 from mdm.fact_order_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where b.date between current_date - interval '30 days' and current_date - interval '1 day' | Analytical | Daily | Insert Into | N/A | N/A
28 | Marketplace | fact_platform_peformance_summary | l1d_otd_time | Average on-time delivery time (in hours) for the last 1 day | 1.0000, 10.1234, 99.9999 | decimal | (6, 4) | N | MDM | mdm.fact_parcel_detail, mdm.dim_date | order_create_time_key, delivered_time_key, date_key | bigint, bigint, bigint | 19, 19, 19 | (delivered_time_key - order_create_time_key)/(count(parcel_id) * 3600.0000) from mdm.fact_parcel_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where a.delivered_time_key is not null and b.date = current_date - interval '1 day' | Analytical | Daily | Insert Into | N/A | N/A
29 | Marketplace | fact_platform_peformance_summary | l7d_otd_time | Average on-time delivery time (in hours) for the last 7 days | 1.0000, 10.1234, 99.9999 | decimal | (6, 4) | N | MDM | mdm.fact_parcel_detail, mdm.dim_date | order_create_time_key, delivered_time_key, date_key | bigint, bigint, bigint | 19, 19, 19 | (delivered_time_key - order_create_time_key)/(count(parcel_id) * 3600.0000) from mdm.fact_parcel_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where a.delivered_time_key is not null and b.date between current_date - interval '7 days' and current_date - interval '1 day' | Analytical | Daily | Insert Into | N/A | N/A
30 | Marketplace | fact_platform_peformance_summary | l30d_otd_time | Average on-time delivery time (in hours) for the last 30 days | 1.0000, 10.1234, 99.9999 | decimal | (6, 4) | N | MDM | mdm.fact_parcel_detail, mdm.dim_date | order_create_time_key, delivered_time_key, date_key | bigint, bigint, bigint | 19, 19, 19 | (delivered_time_key - order_create_time_key)/(count(parcel_id) * 3600.0000) from mdm.fact_parcel_detail a join mdm.dim_date b on a.order_create_date_key = b.date_key where a.delivered_time_key is not null and b.date between current_date - interval '30 days' and current_date - interval '1 day' | Analytical | Daily | Insert Into | N/A | N/A
31 | Warehouse | dim_warehouse | wh_key | Foreign key linking to the dim_warehouse table to identify the assigned warehouse, if any | 1,2,3 | serial | 3 | N | N/A | N/A | N/A | N/A | N/A | system generated | N/A | N/A | N/A | N/A | N/A
32 | Warehouse | dim_warehouse | wh_id | Identification for warehouse (natural key) | 1,2,3 | smallint | 3 | N | WMS | wms.outbound_order | wh_id | smallint | 3 | distinct(wh_id) from wms.outbound_order | Detail | Monthly | Insert Into | No | N/A
33 | Warehouse | dim_warehouse | wh_name | Designated name of the warehouse | LUZ01, VIZ02, MIN03 | varchar | 5 | N | Flat File Ingestion | wh_information_ingestion | wh_name | varchar | 5 | wh_name from wh_information_ingestion | Detail | Monthly | Insert Into | No | N/A
34 | Warehouse | dim_warehouse | wh_region | Warehouse's geographic region address | Luzon, Visayas, Mindanao | varchar | 30 | N | Flat File Ingestion | wh_information_ingestion | wh_region | varchar | 30 | wh_region from wh_information_ingestion | Detail | Monthly | Insert Into | No | N/A
35 | Warehouse | dim_warehouse | wh_city | Warehouse's city address | Mandaluyong, Bansud, Manila | varchar | 30 | N | Flat File Ingestion | wh_information_ingestion | wh_city | varchar | 30 | wh_city from wh_information_ingestion | Detail | Monthly | Insert Into | No | N/A
36 | Warehouse | dim_warehouse | wh_brgy | Warehouse's barangay address | Wack-Wack, Alcadesma, Poblacion | varchar | 30 | N | Flat File Ingestion | wh_information_ingestion | wh_brgy | varchar | 30 | wh_brgy from wh_information_ingestion | Detail | Monthly | Insert Into | No | N/A
37 | Warehouse | dim_warehouse | wh_postal_code | Postal code of the warehouse's location | 123456782468 | smallint | 4 | N | Flat File Ingestion | wh_information_ingestion | wh_postal_code | smallint | 4 | wh_postal_code from wh_information_ingestion | Detail | Monthly | Insert Into | No | N/A
38 | Warehouse | dim_warehouse | total_land_area | Total land area of the warehouse in sq meters | 1000000.1234, 10000000.1234, 10000000.1234 | decimal | (12, 4) | N | Flat File Ingestion | wh_information_ingestion | total_land_area | decimal | (12, 4) | total_land_area from wh_information_ingestion | Detail | Monthly | Insert Into | Rarely | SCD Type 2
39 | Warehouse | dim_warehouse | operating_hours | Operational warehouse of the warehouse | 10:00 - 20:00, 12:00 - 22:30, 8:30 - 80:00 | varchar | 14 | N | Flat File Ingestion | wh_information_ingestion | operating_hours | varchar | 14 | operating_hours from wh_information_ingestion | Detail | Monthly | Insert Into | Rarely | SCD Type 2
40 | Warehouse | dim_warehouse | is_active | 1 if active, 0 if not operational | 1, 0 | boolean |  | N | Flat File Ingestion | wh_information_ingestion | is_active | boolean |  | is_active from wh_information_ingestion | Detail | Monthly | Insert Into | Rarely | SCD Type 2

## Physical Design
No | Data Mart | Table Name | Column Name | Data Type
1 | MDM | dim_buyer | buyer_key | INT
2 | MDM | dim_buyer | user_id | INT
3 | MDM | dim_buyer | user_birthdate | DATE
4 | MDM | dim_buyer | present_address_region | STRING
5 | MDM | dim_buyer | present_address_city | STRING
6 | MDM | dim_buyer | present_address_brgy | STRING
7 | MDM | dim_buyer | sex | STRING
8 | MDM | dim_buyer | account_create_time | DATETIME
9 | MDM | dim_buyer | user_email | STRING
10 | MDM | dim_buyer | user_contact_no | STRING
11 | MDM | dim_buyer | is_active | BOOLEAN
12 | MDM | dim_buyer | last_modified_time | DATETIME
13 | MDM | dim_date | date_key | INT
14 | MDM | dim_date | date | DATE
15 | MDM | dim_date | quarter | INT
16 | MDM | dim_date | year | INT
17 | MDM | dim_date | month | INT
18 | MDM | dim_date | day | INT
19 | MDM | dim_date | day_of_week | INT
20 | MDM | dim_date | day_type | STRING
21 | MDM | dim_date | is_holiday | BOOLEAN
22 | MDM | dim_date | is_campaign_day | BOOLEAN
23 | MDM | dim_date | is_salary_day | BOOLEAN
24 | MDM | dim_item | sku_key | INT
25 | MDM | dim_item | sku_id | INT
26 | MDM | dim_item | shop_id | INT
27 | MDM | dim_item | listing_id | INT
28 | MDM | dim_item | listing_name | STRING
29 | MDM | dim_item | listing_description | STRING
30 | MDM | dim_item | category_lvl_1 | STRING
31 | MDM | dim_item | category_lvl_2 | STRING
32 | MDM | dim_item | model_id | INT
33 | MDM | dim_item | item_id | INT
34 | MDM | dim_item | model_name | STRING
35 | MDM | dim_item | item_description | STRING
36 | MDM | dim_item | weight | DECIMAL
37 | MDM | dim_item | length | DECIMAL
38 | MDM | dim_item | width | DECIMAL
39 | MDM | dim_item | height | DECIMAL
40 | MDM | dim_item | item_price | DECIMAL
41 | MDM | dim_item | is_active | BOOLEAN
42 | MDM | dim_item | create_time | DATETIME
43 | MDM | dim_item | banned_time | DATETIME
44 | MDM | dim_item | last_modified_time | DATETIME
45 | MDM | dim_item | is_wh | BOOLEAN
46 | MDM | dim_location | loc_key | INT
47 | MDM | dim_location | region | STRING
48 | MDM | dim_location | city | STRING
49 | MDM | dim_location | brgy | STRING
50 | MDM | dim_location | postal_code | STRING
51 | MDM | dim_operator | operator_key | INT
52 | MDM | dim_operator | operator_name | STRING
53 | MDM | dim_operator | courier_id | INT
54 | MDM | dim_operator | company_name | STRING
55 | MDM | dim_operator | create_time | DATETIME
56 | MDM | dim_order | order_key | INT
57 | MDM | dim_order | order_id | INT
58 | MDM | dim_order | parcel_id | INT
59 | MDM | dim_order | checkout_id | INT
60 | MDM | dim_order_parcel | order_key | INT
61 | MDM | dim_order_parcel | order_id | INT
62 | MDM | dim_order_parcel | parcel_id | INT
63 | MDM | dim_order_parcel | checkout_id | INT
64 | MDM | dim_parcel_status | parcel_status_key | INT
65 | MDM | dim_parcel_status | order_status | STRING
66 | MDM | dim_parcel_status | logistics_status | STRING
67 | MDM | dim_parcel_status | fe_status | STRING
68 | MDM | dim_parcel_status | be_status | STRING
69 | MDM | dim_parcel_status | warehouse_status | STRING
70 | MDM | dim_payment | payment_option_key | INT
71 | MDM | dim_payment | payment_option_id | INT
72 | MDM | dim_payment | user_id | INT
73 | MDM | dim_payment | payment_channel_id | INT
74 | MDM | dim_payment | channel_name | STRING
75 | MDM | dim_payment | is_current | BOOLEAN
76 | WDM | dim_purchase_order_asn | asn_key | INT
77 | WDM | dim_purchase_order_asn | asn_id | INT
78 | WDM | dim_purchase_order_asn | po_id | INT
79 | WDM | dim_purchase_order_asn | wh_id | INT
80 | WDM | dim_purchase_order_asn | sku_id | INT
81 | WDM | dim_purchase_order_asn | supplier_id | INT
82 | MDM | dim_seller | seller_key | INT
83 | MDM | dim_seller | user_id | INT
84 | MDM | dim_seller | shop_id | INT
85 | MDM | dim_seller | user_birthdate | DATE
86 | MDM | dim_seller | shop_name | STRING
87 | MDM | dim_seller | shop_category | STRING
88 | MDM | dim_seller | shop_create_time | DATETIME
89 | MDM | dim_seller | user_email | STRING
90 | MDM | dim_seller | user_contact_no | STRING
91 | MDM | dim_seller | is_active | BOOLEAN
92 | MDM | dim_seller | last_modified_time | DATETIME
93 | MDM | dim_shipping | shipping_channel_key | INT
94 | MDM | dim_shipping | shipping_channel_id | INT
95 | MDM | dim_shipping | courier_id | INT
96 | MDM | dim_shipping | company_name | STRING
97 | MDM | dim_shipping | channel_name | STRING
98 | WDM | dim_staff | staff_key | INT
99 | WDM | dim_staff | staff_id | INT
100 | WDM | dim_staff | agency | STRING
101 | WDM | dim_staff | staff_email | STRING
102 | WDM | dim_staff | name_first | STRING
103 | WDM | dim_staff | name_middle | STRING
104 | WDM | dim_staff | name_family | STRING
105 | WDM | dim_staff | birthdate | DATE
106 | WDM | dim_staff | account_create_time | DATETIME
107 | WDM | dim_staff | contact_number | STRING
108 | WDM | dim_staff | is_current | BOOLEAN
109 | WDM | dim_storage | storage_key | INT
110 | WDM | dim_storage | lane_number | STRING
111 | WDM | dim_storage | rack_number | STRING
112 | WDM | dim_storage | layer_number | STRING
113 | WDM | dim_storage | wh_id | INT
114 | WDM | dim_storage | latest_flag | BOOLEAN
115 | WDM | dim_supplier | supplier_key | INT
116 | WDM | dim_supplier | supplier_id | INT
117 | WDM | dim_supplier | supplier_name | STRING
118 | WDM | dim_supplier | address | STRING
119 | WDM | dim_supplier | contact_person | STRING
120 | WDM | dim_supplier | contact_no | STRING
121 | WDM | dim_supplier | create_time | DATETIME
122 | WDM | dim_supplier | is_active | BOOLEAN
123 | WDM | dim_task | task_key | INT
124 | WDM | dim_task | task_id | INT
125 | WDM | dim_task | process | STRING
126 | WDM | dim_task | task_name | STRING
127 | MDM | dim_time | time_key | INT
128 | MDM | dim_time | timestamp | DATETIME
129 | MDM | dim_time | date | DATE
130 | MDM | dim_time | quarter | INT
131 | MDM | dim_time | year | INT
132 | MDM | dim_time | month | INT
133 | MDM | dim_time | day | INT
134 | MDM | dim_time | time | TIME
135 | MDM | dim_time | hour | INT
136 | MDM | dim_time | minute | INT
137 | MDM | dim_time | second | INT
138 | MDM | dim_time | day_of_week | INT
139 | MDM | dim_time | day_type | STRING
140 | MDM | dim_time | is_holiday | BOOLEAN
141 | MDM | dim_time | is_campaign_day | BOOLEAN
142 | MDM | dim_voucher | voucher_key | INT
143 | MDM | dim_voucher | voucher_id | INT
144 | MDM | dim_voucher | voucher_code | STRING
145 | MDM | dim_voucher | voucher_type | STRING
146 | MDM | dim_voucher | promotion_id | INT
147 | MDM | dim_voucher | promotion_description | STRING
148 | MDM | dim_voucher | promotion_start_time | DATETIME
149 | MDM | dim_voucher | promotion_end_time | DATETIME
150 | MDM | dim_voucher | voucher_description | STRING
151 | MDM | dim_voucher | create_time | DATETIME
152 | MDM | dim_voucher | valid_start_time | DATETIME
153 | MDM | dim_voucher | valid_end_time | DATETIME
154 | MDM | dim_voucher | is_platform_coverage | BOOLEAN
155 | MDM | dim_voucher | is_shop_sponsored | BOOLEAN
156 | MDM | dim_voucher | is_platform_sponsored | BOOLEAN
157 | MDM | dim_voucher | pcnt_discount | DECIMAL
158 | MDM | dim_voucher | pcnt_min_spend | DECIMAL
159 | MDM | dim_voucher | pcnt_cap | DECIMAL
160 | MDM | dim_voucher | abs_discount | DECIMAL
161 | MDM | dim_voucher | abs_min_spend | DECIMAL
162 | MDM | dim_voucher | abs_cap | DECIMAL
163 | MDM | dim_voucher | is_active | BOOLEAN
164 | MDM | dim_voucher_mix | voucher_mix_key | INT
165 | MDM | dim_voucher_mix | voucher_ids | STRING
166 | MDM | dim_voucher_mix | voucher_codes | STRING
167 | WDM | dim_warehouse | wh_key | INT
168 | WDM | dim_warehouse | wh_id | INT
169 | WDM | dim_warehouse | wh_name | STRING
170 | WDM | dim_warehouse | wh_region | STRING
171 | WDM | dim_warehouse | wh_city | STRING
172 | WDM | dim_warehouse | wh_brgy | STRING
173 | WDM | dim_warehouse | wh_postal_code | STRING
174 | WDM | dim_warehouse | total_land_area | DECIMAL
175 | WDM | dim_warehouse | operating_hours | STRING
176 | WDM | dim_warehouse | is_active | BOOLEAN
177 | WDM | fact_attendance_snapshot | attendance_key | INT
178 | WDM | fact_attendance_snapshot | attendance_id | INT
179 | WDM | fact_attendance_snapshot | wh_key | INT
180 | WDM | fact_attendance_snapshot | staff_key | INT
181 | WDM | fact_attendance_snapshot | date_key | INT
182 | WDM | fact_attendance_snapshot | time_in_key | INT
183 | WDM | fact_attendance_snapshot | time_out_key | INT
184 | WDM | fact_inbound_sku_detail | asn_key | INT
185 | WDM | fact_inbound_sku_detail | supplier_key | INT
186 | WDM | fact_inbound_sku_detail | wh_key | INT
187 | WDM | fact_inbound_sku_detail | storage_key | INT
188 | WDM | fact_inbound_sku_detail | sku_key | INT
189 | WDM | fact_inbound_sku_detail | expected_qty | INT
190 | WDM | fact_inbound_sku_detail | received_qty | INT
191 | WDM | fact_inbound_sku_detail | po_create_time_key | INT
192 | WDM | fact_inbound_sku_detail | asn_arrived_time_key | INT
193 | WDM | fact_inbound_task_detail | task_key | INT
194 | WDM | fact_inbound_task_detail | wh_key | INT
195 | WDM | fact_inbound_task_detail | asn_key | INT
196 | WDM | fact_inbound_task_detail | sku_key | INT
197 | WDM | fact_inbound_task_detail | staff_key | INT
198 | WDM | fact_inbound_task_detail | task_start_time_key | INT
199 | WDM | fact_inbound_task_detail | task_end_time_key | INT
200 | MDM | fact_order_detail | order_key | INT
201 | MDM | fact_order_detail | buyer_key | INT
202 | MDM | fact_order_detail | seller_key | INT
203 | MDM | fact_order_detail | voucher_mix_key | INT
204 | MDM | fact_order_detail | voucher_total_value | DECIMAL
205 | MDM | fact_order_detail | payment_option_key | INT
206 | MDM | fact_order_detail | shipping_fee | DECIMAL
207 | MDM | fact_order_detail | gmv | DECIMAL
208 | MDM | fact_order_detail | order_create_date_key | DATE
209 | MDM | fact_order_detail | order_create_time_key | TIME
210 | MDM | fact_order_detail | unique_sku_count | INT
211 | MDM | fact_order_detail | total_sku_qty | INT
212 | MDM | fact_order_detail | wh_key | INT
213 | MDM | fact_order_detail | parcel_count | INT
214 | MDM | fact_order_item_detail | order_key | INT
215 | MDM | fact_order_item_detail | sku_key | INT
216 | MDM | fact_order_item_detail | buyer_key | INT
217 | MDM | fact_order_item_detail | seller_key | INT
218 | MDM | fact_order_item_detail | qty | INT
219 | MDM | fact_order_item_detail | order_create_date_key | DATE
220 | MDM | fact_order_item_detail | order_create_time_key | TIME
221 | MDM | fact_order_item_detail | total_gmv | DECIMAL
222 | MDM | fact_order_item_detail | unit_gmv | DECIMAL
223 | MDM | fact_order_item_detail | wh_key | INT
224 | WDM | fact_outbound_order_detail | forder_key | INT
225 | WDM | fact_outbound_order_detail | wh_key | INT
226 | WDM | fact_outbound_order_detail | parcel_status_key | INT
227 | WDM | fact_outbound_order_detail | order_create_time_key | INT
228 | WDM | fact_outbound_order_detail | order_outbound_time_key | INT
229 | WDM | fact_outbound_order_detail | ship_by_date_key | INT
230 | WDM | fact_outbound_order_detail | shipping_channel_key | INT
231 | WDM | fact_outbound_sku_detail | forder_key | INT
232 | WDM | fact_outbound_sku_detail | sku_key | INT
233 | WDM | fact_outbound_sku_detail | qty | INT
234 | WDM | fact_outbound_sku_detail | wh_key | INT
235 | WDM | fact_outbound_sku_detail | order_create_time_key | INT
236 | WDM | fact_outbound_sku_detail | order_outbound_time_key | INT
237 | WDM | fact_outbound_sku_detail | ship_by_date_key | INT
238 | WDM | fact_outbound_sku_detail | shipping_channel_key | INT
239 | WDM | fact_outbound_task_detail | task_key | INT
240 | WDM | fact_outbound_task_detail | wh_key | INT
241 | WDM | fact_outbound_task_detail | forder_key | INT
242 | WDM | fact_outbound_task_detail | sku_key | INT
243 | WDM | fact_outbound_task_detail | sku_qty | INT
244 | WDM | fact_outbound_task_detail | staff_key | INT
245 | WDM | fact_outbound_task_detail | task_start_time_key | INT
246 | WDM | fact_outbound_task_detail | task_end_time_key | INT
247 | MDM | fact_parcel_detail | forder_key | INT
248 | MDM | fact_parcel_detail | buyer_key | INT
249 | MDM | fact_parcel_detail | seller_key | INT
250 | MDM | fact_parcel_detail | shipping_channel_key | INT
251 | MDM | fact_parcel_detail | parcel_status_key | INT
252 | MDM | fact_parcel_detail | pickup_time_key | TIME
253 | MDM | fact_parcel_detail | cancel_time_key | TIME
254 | MDM | fact_parcel_detail | delivered_time_key | TIME
255 | MDM | fact_parcel_detail | ship_by_date_key | DATE
256 | MDM | fact_parcel_detail | order_create_date_key | DATE
257 | MDM | fact_parcel_detail | order_create_time_key | TIME
258 | MDM | fact_parcel_detail | shipping_fee | DECIMAL
259 | MDM | fact_parcel_detail | unique_sku_count | INT
260 | MDM | fact_parcel_detail | total_sku_count | INT
261 | MDM | fact_parcel_detail | gmv | DECIMAL
262 | MDM | fact_parcel_detail | wh_key | INT
263 | MDM | fact_parcel_status_snapshot | time_key | TIME
264 | MDM | fact_parcel_status_snapshot | forder_key | INT
265 | MDM | fact_parcel_status_snapshot | parcel_status_key | INT
266 | MDM | fact_parcel_status_snapshot | loc_key | INT
267 | MDM | fact_parcel_status_snapshot | operator_key | INT
268 | MDM | fact_platform_performance_summary | date_key | DATE
269 | MDM | fact_platform_performance_summary | l1d_ado | DECIMAL
270 | MDM | fact_platform_performance_summary | l7d_ado | DECIMAL
271 | MDM | fact_platform_performance_summary | l30d_ado | DECIMAL
272 | MDM | fact_platform_performance_summary | l1d_adgmv | DECIMAL
273 | MDM | fact_platform_performance_summary | l7d_adgmv | DECIMAL
274 | MDM | fact_platform_performance_summary | l30d_adgmv | DECIMAL
275 | MDM | fact_platform_performance_summary | l1d_avg_active_buyers | INT
276 | MDM | fact_platform_performance_summary | l7d_avg_active_buyers | INT
277 | MDM | fact_platform_performance_summary | l30d_avg_active_buyers | INT
278 | MDM | fact_platform_performance_summary | l1d_avg_active_shops | INT
279 | MDM | fact_platform_performance_summary | l7d_avg_active_shops | INT
280 | MDM | fact_platform_performance_summary | l30d_avg_active_shops | INT
281 | MDM | fact_platform_performance_summary | l1d_otd_time | DECIMAL
282 | MDM | fact_platform_performance_summary | l7d_otd_time | DECIMAL
283 | MDM | fact_platform_performance_summary | l30d_otd_time | DECIMAL
284 | MDM | fact_seller_performance_summary | date_key | DATE
285 | MDM | fact_seller_performance_summary | shop_id | INT
286 | MDM | fact_seller_performance_summary | l1d_ado | DECIMAL
287 | MDM | fact_seller_performance_summary | l7d_ado | DECIMAL
288 | MDM | fact_seller_performance_summary | l30d_ado | DECIMAL
289 | MDM | fact_seller_performance_summary | l90d_ado | DECIMAL
290 | MDM | fact_seller_performance_summary | l1d_adgmv | DECIMAL
291 | MDM | fact_seller_performance_summary | l7d_adgmv | DECIMAL
292 | MDM | fact_seller_performance_summary | l30d_adgmv | DECIMAL
293 | MDM | fact_seller_performance_summary | l90d_adgmv | DECIMAL
294 | MDM | fact_sku_performance_summary | date_key | DATE
295 | MDM | fact_sku_performance_summary | sku_id | INT
296 | MDM | fact_sku_performance_summary | l1d_ado | DECIMAL
297 | MDM | fact_sku_performance_summary | l7d_ado | DECIMAL
298 | MDM | fact_sku_performance_summary | l30d_ado | DECIMAL
299 | MDM | fact_sku_performance_summary | l90d_ado | DECIMAL
300 | MDM | fact_sku_performance_summary | l1d_adgmv | DECIMAL
301 | MDM | fact_sku_performance_summary | l7d_adgmv | DECIMAL
302 | MDM | fact_sku_performance_summary | l30d_adgmv | DECIMAL
303 | MDM | fact_sku_performance_summary | l90d_adgmv | DECIMAL
304 | WDM | fact_staff_prod_summary | staff_key | INT
305 | WDM | fact_staff_prod_summary | date_key | INT
306 | WDM | fact_staff_prod_summary | wh_key | INT
307 | WDM | fact_staff_prod_summary | total_items | INT
308 | WDM | fact_staff_prod_summary | total_manhours | DECIMAL
309 | WDM | fact_staff_prod_summary | total_active_manhours | DECIMAL
310 | WDM | fact_staff_prod_summary | prod_rate | DECIMAL
311 | WDM | fact_staff_prod_summary | idle_rate | DECIMAL
312 | WDM | fact_storage_inventory_snapshot | storage_tracking_key | INT
313 | WDM | fact_storage_inventory_snapshot | time_key | INT
314 | WDM | fact_storage_inventory_snapshot | date_key | INT
315 | WDM | fact_storage_inventory_snapshot | storage_key | INT
316 | WDM | fact_storage_inventory_snapshot | wh_key | INT
317 | WDM | fact_storage_inventory_snapshot | sku_key | INT
318 | WDM | fact_storage_inventory_snapshot | stock_qty | INT
319 | WDM | fact_warehouse_summary | date_key | INT
320 | WDM | fact_warehouse_summary | wh_key | INT
321 | WDM | fact_warehouse_summary | total_items | INT
322 | WDM | fact_warehouse_summary | total_manhours | DECIMAL
323 | WDM | fact_warehouse_summary | total_active_manhours | DECIMAL
324 | WDM | fact_warehouse_summary | l1d_ado | DECIMAL
325 | WDM | fact_warehouse_summary | l7d_ado | DECIMAL
326 | WDM | fact_warehouse_summary | l30d_ado | DECIMAL
327 | WDM | fact_warehouse_summary | l1d_adi | DECIMAL
328 | WDM | fact_warehouse_summary | l7d_adi | DECIMAL
329 | WDM | fact_warehouse_summary | l30d_adi | DECIMAL
330 | WDM | fact_warehouse_summary | l1d_prod_rate | DECIMAL
331 | WDM | fact_warehouse_summary | l7d_prod_rate | DECIMAL
332 | WDM | fact_warehouse_summary | l30d_prod_rate | DECIMAL
333 | WDM | fact_warehouse_summary | l1d_idle_rate | DECIMAL
334 | WDM | fact_warehouse_summary | l14d_idle_rate | DECIMAL
335 | WDM | fact_warehouse_summary | l30d_idle_rate | DECIMAL